## Slide 1: International Urban cooperation
C3 PAIRING REGion cioeste & REGION bielsko-biała
Patrycja Węgrzyn & Carlos Abrao|| pwegrzyn@arrsa.pl & abrao.carlos@gmail.com

## Slide 2: OUTLINE
Pairing objective
1
priorities
3
Key actions
5
Main milestones
2
Transformative activities
4
timeline
6
7
LESSONS LEARNED
Dos & don’ts
8

## Slide 3: PAIRING OBJECTIVE
01

## Slide 4: Pairing OBJECTIVE
Establish cooperation for economic development in the area of ICT
  to promote internationalisation of companies from both regions
  to use the two regions as HUBs to access the Brazilian and Polish markets
  to open the Latin America and European markets to both regions

## Slide 5: MAIN MILESTONES
02

## Slide 6: MILESTONES
  Before the first mission in Poland: drafting the cooperation
  Kick of meeting – Brussels, November 2017: definition of the mutual intrest and area of cooperation
  SWOT analysis of the state of the art: how does the ICT sector looks like in both regions? – questionnaire
  First official online conference: city – education – business representatives from both regions
  Working in regions: assesment of the questionnaire, indication of firms to be involved in the project
  Niches of cooperation: clarification of the areas of mutual intrest

## Slide 7: MILESTONES
First mission in Poland – May 2018:
  Meetings between te representatives of entities that have expressed their will of cooperation:
    Local government
    Universities
    Start-up and business support environment
    Firms
  signing the Memorandum of Understanding by representatives of project partners – CIOESTE and ARRSA
  Roadmap of cooperation: niches, firms and ways of cooperation indicated

## Slide 8: MILESTONES
  After the mission in Poland – before the mission in Brazil:
  Weekly Skype calls between project partners
  Bilateral on-line meetings of firms: CIOESTE and ARRSA as a facilitators of cooperation
  Details of the roadmap: towards the action plan
  Preparation of the second mission agenda

## Slide 9: PRIORITIES
03

## Slide 10: PRIORITIES
  Internationalisation of local SMEs
  Build critical mass by developing knowledge and required skills and capabilities for current and future jobs
  Develop an ecosystem that fosters innovation

## Slide 11: TRANSFORMATIVE Activities
04

## Slide 12: TRANSFORMATIVE ACTIVITIES
Internationalisation of local SMEs
  Establish bilateral cooperation between firms of both regions
  Develop for CIOESTE an innovation/ competition strategy and an associated plan for entering international markets with support from Bielsko-Biala
  Share the methodology of organising international ICT event – following the experience of CIOESTE

## Slide 13: TRANSFORMATIVE ACTIVITIES
Build critical mass by developing knowledge and required skills and capabilities for current and future jobs
  Establish bilateral cooperation between regional and international universities and research centres
  Develop a joint knowledge platform for communication and exchange of business opportunities (i.e. demand and offer) in both regions

## Slide 14: TRANSFORMATIVE ACTIVITIES
Develop an ecosystem that fosters innovation
  Promote regionally international trend and business ICT events in order to both influence and stay up to date with current and future technological developments
  Test new solutions for innovation public policies that stimulates start-ups, accelerators and incubators

## Slide 15: KEY ACTIONS
05

## Slide 16: KEY ACTIONS
Mapping of the ICT business in both regions
Indication of the niches of cooperation
Regular on-line meetings
Participation in first I.OESTE event – introducing ARRSA to Brazilian entrepreneurs
Bringing together entities interested in cooperaion
Mission in Poland – signing MoU

## Slide 17: KEY ACTIONS
Presentation of the companies: bilateral meetings, presentations of products, services
Roadmap of activities
Participation in the second I.OESTE during the Polish mission in Brazil
  Giving the opportunity to face-to-face meetings between Polish and Brazilian entrprenuers

## Slide 18: TIMELINE
Main Milestones | Sector / Area / Theme | Key objective of the Pairing Action |  |  | Timeline (1 year) |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
milestone | Sector / Area / Theme 1 | Overall objective of the pairing action |  |  |  |  |  |  |  |  |  |  |  |  |  | 
milestone |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
milestone |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
milestone |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
milestone |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
milestone |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
milestone |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Key objective of the Pairing Action | Sector / Area / Theme | Priorities | Transformative Activies | Actions | Timeline (1 year) |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Overall objective of the pairing action | Sector / Area / Theme 1 | Priority 1 | Transformative activity | Action |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Action |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Transformative activity | Action |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Priority 2 | Transformative activity | Action |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Action |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Transformative activity | Action |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Priority n | Transformative activity | Action |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Action |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Transformative activity | Action |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Action |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 19: LESSONS LEARNED
07

## Slide 20: LESSONS LEARNED
  How to prepare innovation strategy for the region?
  How to organise high-level ICT event?
  Bringing the knowledge about the regions and role of CIOESTE and ARRSA as a businnes suport organisations to entrepreneurs
  Use the trust to our institutions (CIOESTE and ARRSA) as a bridge to build business suport environment in both regions
  Use the universities education capacity to keep talents and high-level employees in the regions
  Use the international events to make a brand

## Slide 21: DOS & DON’TS
08

## Slide 22: DOS & DON’TS
Follow up projects – information at the begining of cooperation what are the financing possibilities
Budget for the implementation of the project in regions – Staff, promotion, local events etc.
Avoid top-down approach
Our institutions only as a facilitators, not managers of business cooperation